## Milestone and Complexity Form
Milestones and Complexity
Legend
Dropdown selection
User Input required (free text)
Program
Project
Complexity
Milestone |  | Date
1st 40% claim will be submitted
Detailed design completed
Land access agreements will be concluded to enable construction to commence
Project clearances will be received to enable construction to commence
Service relocations will be completed to enable construction to commence
Main Roads regulatory approvals will be received
Contracts will be let or in house construction will commence
2nd 40% claim will be submitted
Practical completion
Final claim will be submitted
Signed and endorsed by Senior Technical Manager |  | Date
Note on A18: Application of advance payment equal to 40% of the approved project allocation supported by a Progress Payment Certificate
Note on A19: Council approval of finalised drawings and technical specifications and endorsed as IFC
Note on A20: The land acquisition process is undertaken with land owners and other stakeholders and approved prior to construction
Note on A21: • Council approval obained • Community consultation undertaken and finalised • Application to undertake works near or at MRWA Road Reserve reviewed and approved • Any other clearances/permits/surveys not already provided for in the milestones approved
Note on A22: Western Power, ATCO Gas, Water Corporation, Telstra applications have been approved
Note on A23: • RNO ¦ Traffic Services approval Review and approval of the traffic signal modifications and signs and pavement makings • Road & Traffic Engineering Review of the road design, traffic engineering, drainage, barriers etc • Electrical Review and advice on lighting and ITS requirements • Structures Review technical issues for structures and waterways
Note on A24: Delivery in-house or tenders awarded and delivery scheduled for commencement
Note on A25: Certification that incurred expenditure on the project has exceeded 40% of the approved project allocation with a Progress Payment Certificate
Note on A26: Work is deemed to be substantially complete and is open to traffic
Note on A27: On completion of the project, a Certficate of Completion is submitted showing the Final Total Project Cost of the project and the balance of funds to be released / refunded.

## DataValidations (hidden)
Program
24/25 Road Rehabilitation Submission
24/25 Road Improvement Submission
24/25 State Black Spot Submission
24/25 Australian Government Black Spot Submission
24/25 State and Australian Government Black Spot Submission
Complexity
Complex
Fully designed, costed with all third party approvals received
Date
Not applicable
2020-07-01
2020-08-01
2020-09-01
2020-10-01
2020-11-01
2020-12-01
2021-01-01
2021-02-01
2021-03-01
2021-04-01
2021-05-01
2021-06-01
2021-07-01
2021-08-01
2021-09-01
2021-10-01
2021-11-01
2021-12-01
2022-01-01
2022-02-01
2022-03-01
2022-04-01
2022-05-01
2022-06-01
2022-07-01
2022-08-01
2022-09-01
2022-10-01
2022-11-01
2022-12-01
2023-01-01
2023-02-01
2023-03-01
2023-04-01
2023-05-01
2023-06-01
2023-07-01
2023-08-01
2023-09-01
2023-10-01
2023-11-01
2023-12-01
2024-01-01
2024-02-01
2024-03-01
2024-04-01
2024-05-01
2024-06-01
2024-07-01
2024-08-01
2024-09-01
2024-10-01
2024-11-01
2024-12-01
2025-01-01
2025-02-01
2025-03-01
2025-04-01
2025-05-01
2025-06-01
2025-07-01
2025-08-01
2025-09-01
2025-10-01
2025-11-01
2025-12-01
2026-01-01
2026-02-01
2026-03-01
2026-04-01
2026-05-01
2026-06-01
2026-07-01
2026-08-01
2026-09-01
2026-10-01
2026-11-01
2026-12-01
2027-01-01
2027-02-01
2027-03-01
2027-04-01
2027-05-01
2027-06-01
2027-07-01
2027-08-01
2027-09-01
2027-10-01
2027-11-01
2027-12-01
2028-01-01
2028-02-01
2028-03-01
2028-04-01
2028-05-01
2028-06-01
2028-07-01
2028-08-01
2028-09-01
2028-10-01
2028-11-01
2028-12-01
2029-01-01
2029-02-01
2029-03-01
2029-04-01
2029-05-01
2029-06-01
2029-07-01
2029-08-01
2029-09-01
2029-10-01
2029-11-01
2029-12-01
2030-01-01
2030-02-01
2030-03-01
2030-04-01
2030-05-01
2030-06-01
2030-07-01
2030-08-01
2030-09-01
2030-10-01
2030-11-01
2030-12-01
2031-01-01
2031-02-01
2031-03-01
2031-04-01
2031-05-01
2031-06-01
2031-07-01
2031-08-01
2031-09-01
2031-10-01
2031-11-01
2031-12-01
2032-01-01
2032-02-01
2032-03-01
2032-04-01
2032-05-01
2032-06-01
2032-07-01
2032-08-01
2032-09-01
2032-10-01
2032-11-01
2032-12-01
2033-01-01
2033-02-01
2033-03-01
2033-04-01
2033-05-01
2033-06-01
2033-07-01
2033-08-01
2033-09-01
2033-10-01
2033-11-01
2033-12-01
2034-01-01
2034-02-01
2034-03-01
2034-04-01
2034-05-01
2034-06-01
2034-07-01
2034-08-01
2034-09-01
2034-10-01
2034-11-01
2034-12-01
2035-01-01
2035-02-01
2035-03-01
2035-04-01
2035-05-01
2035-06-01